Vehicle Funding Close Packet

Wheatland pilot funding, vehicle, authority, insurance, and approval controls

DRAFT - NOT EFFECTIVE UNTIL REVIEWED, APPROVED, DATED, AND SIGNED

Prepared for VILIGANS COMMAND CORPORATION as an internal and review-ready draft packet. This packet supports quote, fit, timing, sponsor, and readiness discussions. It does not authorize sending, signing, applications, credit pulls, deposits, insurance binding, vehicle commitments, filings, invoices, restricted funds, or paid passenger service.

# Executive Target

| Target | Current position | Evidence needed |
| --- | --- | --- |
| Funding by August 9, 2026 | Realistic for commitments, bridge support, sponsor/readiness pledges, or preapproval; not realistic for grant cash. | Signed pledge, payment proof, approved bridge memo, lender preapproval, or written term sheet. |
| Pilot vehicle by August 15, 2026 | Possible only through an immediately available accessible van purchase/lease, short-term rental bridge, or approved partner vehicle. | Written quote or rental confirmation, insurance bindability, WYDOT path, approval memo, and funding source. |
| Paid passenger launch | Not approved by this packet. | Authority, insurance, vehicle, driver, policy, privacy, rate-card, and partner gates complete. |

# Approval Control

| Allowed after CEO approval | Not allowed without separate approval |
| --- | --- |
| Controlled quote, fit, and timing contact with listed vendors, lenders, insurers, WYDOT, and sponsor/anchor targets. | Applications, credit pulls, deposits, vehicle reservations, purchase/lease/rental agreements, insurance bind orders, authority filings, invoices, restricted funds, sponsor logo promises, public launch claims, or paid passenger service. |

# Authority And Insurance Evidence

| Lane | Current evidence | Sprint implication |
| --- | --- | --- |
| WYDOT authority | WYDOT defines contract motor carrier as intrastate transportation of people or property for compensation; WYDOT lists 307-777-4850 for questions. | Call or send the unsent authority question draft before relying on any paid passenger-service plan. |
| MC-100 / Form E | WYDOT MC-100 asks passenger carriers to list passenger count; Form E is required before contract carrier authority approval if applicable. | Insurance conversations must ask whether the carrier can issue Wyoming Form E. |
| Coverage threshold | WYDOT MC-100 lists $750,000 combined single limit for contract carrier liability filings. | Quote conversations should test at least this threshold if the authority path applies. |
| USDOT trigger | WYDOT MC-100 states more than 9 passengers, including the driver, must have a USDOT number. | Keep the first vehicle below that threshold unless VCC intentionally opens the USDOT path. |
| Insurance quote paths | Insureon lists NEMT/paratransit quote support at 800-688-1984; Progressive lists NEMT quote support at 1-888-806-9598 in select states. | Use both as eligibility and bindability checks, not as binding applications. |

# Funding Close Register

| Lane | Target amount | Proof required | Status | Next action |
| --- | --- | --- | --- | --- |
| Vehicle readiness sponsor | $10,000-$25,000 | Signed sponsor commitment or written pledge with amount, payment date, allowed use, and recognition terms | Prepared/not committed | Approve sponsor commitment template and send to top sponsor targets after vehicle/insurance assumptions are grounded. |
| Anchor readiness fee | $5,000-$15,000 | Written readiness-fee commitment, MOU term sheet, or purchase order path with clear non-emergency scope | Prepared/not committed | Use one-page Wheatland offer and commitment template in anchor planning call. |
| Sponsor ride block | $2,500-$10,000 | Written pledge defining ride block purpose, eligible rider category, reporting, and no-launch-before-gates condition | Prepared/not committed | Prepare sponsor-specific amount and recognition option before outreach. |
| Commercial lease preapproval | $999-$1,399 monthly benchmark plus taxes, title, license, freight, insurance deposit, and delivery fees | Written lease/preapproval response showing vehicle class, stock/VIN or available class, total due at delivery, monthly payment, mileage, term, guaranty, required documents, and funding timing | Prepared/not committed | Request preliminary fit and current availability before any application or credit pull. |
| Rental bridge support | $12,000-$20,000 | Funds received or approved written bridge authorization with repayment/restriction terms | Open | Prepare bridge approval memo only if rental availability and insurance requirements are confirmed. |
| Low-cost used vehicle stack | $20,000-$35,000 plus financing if needed | Vehicle quote under target band, insurance bindability, down payment source, approval memo | Prepared/not committed | Call MobilityWorks Aurora about stock KR692569A and commercial-use quote path. |
| Vehicle financing / lease | $20,000-$80,000 purchasing power | Preapproval or term sheet showing borrower, amount, down payment, rate/range, term, guaranty, collateral, and funding timing | Prepared/not committed | Approve WyoMicro draft and finance calls; collect preliminary fit before any application. |
| Partner vehicle access | In-kind / contract TBD | Written MOU or service agreement showing vehicle, driver, insurance, authority, payment, data, and liability roles | Open | Use partner MOU template only after partner confirms capacity and insurance/authority proof. |

# Public Vehicle Shortlist

| Priority | Vendor | Vehicle | Price / terms | Fastest use | Next action |
| --- | --- | --- | --- | --- | --- |
| 1 | MobilityWorks Aurora | Used 2019 Dodge Grand Caravan SXT | $32,991 public listing; coming soon | Purchase/finance path only after written quote and insurance bindability | Call MobilityWorks Aurora and ask whether KR692569A can be quoted for Wheatland business-use diligence. |
| 2 | MobilityWorks Commercial / Aurora | 2019 Dodge Grand Caravan SE | Request pricing | Commercial quote path after price, insurance, and inspection review | Ask commercial team for price, commercial-use terms, securement details, inspection history, and delivery timing. |
| 2A | MobilityWorks Commercial | 2026 Chrysler Voyager commercial vehicle with BraunAbility rear-entry conversion | Public disclosure lists starting lease benchmarks at $999/month for 48 months with 10,000 miles/year or $1,099/month for 48 months with 20,000 miles/year for well-qualified commercial customers; taxes, title, license, freight, and other fees due at delivery | Lease/preapproval path if commercial credit, insurance, authority, and delivery timing line up by August 9 | Ask MobilityWorks Commercial for current Chrysler Voyager lease availability, total due at delivery, credit/preapproval sequence, business-use terms, and timing. |
| 2B | MobilityWorks Commercial | 2026 Ford Transit commercial vehicle with Driverge rear-entry or side-entry conversion | Public disclosure lists starting lease benchmarks at $1,299/month for 48 months with 15,000 miles/year or $1,399/month for 48 months with 25,000 miles/year for well-qualified commercial customers; taxes, title, license, freight, and other fees due at delivery | Lease/preapproval path if commercial credit, insurance, authority, and delivery timing line up by August 9 | Ask MobilityWorks Commercial for current Ford Transit lease availability, total due at delivery, passenger seating/securement, and Wyoming use timing. |
| 3 | MobilityWorks Aurora | Used 2025 Chrysler Pacifica Select (New Conversion) | $61,990 public listing | Purchase/finance path if written quote, financing, and insurance line up by August 9 | Request written quote including total due, financing estimate, warranty, conversion inspection, and commercial-use permission. |
| 4 | MobilityWorks Aurora | New 2026 Chrysler Voyager LX | $64,990 public listing | Purchase/finance path if financing approval is quick | Ask for current total price, delivery timing, commercial-use permissions, and financing/down-payment terms. |
| 5 | MobilityWorks Aurora | Used 2024 Chrysler Pacifica Touring L | $68,995 public listing | Purchase/finance path if quote and insurance are strong | Ask whether RR187391 is available for immediate business-use quote and what deposit holds it. |
| 6 | United Access Wheat Ridge | New 2026 Ford Transit 350 XL | Estimated $86,900 public listing | Purchase/lease/finance path only if financing and insurance are fast | Use existing United Access draft and follow up by phone for written quote, seating, securement, commercial use, and delivery timing. |
| 7 | MobilityWorks Rental Team | Short-term wheelchair-accessible van rental | Rates require quote; public rental page lists CO-Denver/Aurora contact path, rental number (877) 275-4915, side-entry/rear-entry accessible vans, tie-downs, and 150 free miles per day | Dry runs, demos, route checks, and readiness proof if rental terms allow; no paid service without launch gates | Call rental team for August 10-15 availability, business-use rules, insurance requirements, mileage, total cost, and pickup/delivery timing. |

# Sponsor / Readiness Commitment Terms

| Term | Draft control |
| --- | --- |
| Commitment types | Vehicle readiness sponsorship, sponsor-funded local ride block, anchor readiness fee, community access day sponsorship, in-kind support, or letter of support. |
| Allowed uses | Accessible vehicle deposit/rental/lease startup, insurance deposit, inspection, securement, safety kit, registration/use documentation, dispatch/reporting setup, route planning, partner onboarding, and compliance readiness. |
| Recognition | Sponsor recognition only after approval; no logo, vehicle/event placement, public statement, or service-readiness claim without review. |
| Reporting | Non-PHI reporting only: ride requests, completed rides, denied/deferred rides, general service areas, cost summaries, incident-free days, and unmet-need observations. |
| Restrictions | Do not treat a pledge as cash until funds are received or a binding approved written commitment exists. |

# August 9 Go / No-Go Evidence

| Evidence | Minimum standard |
| --- | --- |
| Vehicle option | Written quote or rental confirmation with stock/VIN or rental class, conversion, entry type, securement, mileage, price, total due, timing, and commercial-use rules. |
| Insurance | Broker/carrier guidance that the service model and vehicle can be insured, including required limits, exclusions, driver requirements, and Form E capability if WYDOT requires it. |
| Authority | WYDOT call notes confirming MC-100, Form E, registration, marking, USDOT, and passenger-capacity implications for Wheatland paid passenger service. |
| Funding | Signed pledge, readiness-fee commitment, lender preapproval, approved bridge funds, or microloan/lease path with timing and conditions. |
| Approval | CEO/officer approval of any outreach, quote submission, application, credit pull, deposit, invoice, agreement, or restricted-fund acceptance. |

# CEO Approval Placeholder

Approval requested only for controlled external contact to gather quote, fit, and timing information.

| Approval | Selection |
| --- | --- |
| Controlled external contact only | Yes / No |
| Excluded items or limits |  |
| Authorized signer | ALAWNDUS L. DAVIS, CEO / Founder |
| Signature |  |
| Date |  |